## Year Plan
Month | Goals | Start | End | Status
Sep | Complete Nano program: Project 1 | 2022-09-01 | 2022-03-31 | Done
Nov | Complete Nano program: Project 2 | 2022-10-01 | 2022-11-14 | In Progess
Dec | Complete Nano program: Project 3 | 2022-11-15 | 2022-12-31 | In Progess
Fer | Get certificate AZ-400 Designing and Implementing Microsoft DevOps Solutions from Microsoft |  |  | To do
| Goals | Goals
Sep: Complete Nano program: Project 1
Complete all topic Azure Infrastructure operations
Submit project1
Nov: Complete Nano program: Project 2
Complete all topic Agile Deployment with Azure
Submit Project2
Dec: Complete Nano program: Project 3
Complete all topic Ensuring Quality Releases
Submit Project3
Fer:Get certificate AZ-400 Designing and Implementing Microsoft DevOps Solutions from Microsoft

## Quarter Plan
Quarter 2 | Upskill about devops
Week | <component> | Start | End | Status
2022-05-10 | Continuous Integration Setup | 2022-05-10 | 2022-05-16 | Done
2022-05-17 | Continuous Delivery on Azure | 2022-05-17 | 2022-05-23 | Done
2022-05-24 | Documentation of Work | 2022-05-24 | 2022-05-30 | Done
2022-05-31 | Demo of Work for Submission | 2022-05-31 | 2022-06-06 | Done
2022-06-07 | Review Feedback and do corrective actions based on Feedback | 2022-06-07 |  | In Progess
2022-06-14 | Project Clean up |  |  | To Do
| Goals | Goals
Continuous Integration Setup
CI: Set Up Azure Cloud Shell
Create the Cloud-Based Development Environment
Create Project Scaffolding
Local Test
CI: Configure GitHub Actions
Enable Github Actions
Modify Github Actions yml code
Verify Remote Tests pass
Screen Shot and update README.md
Continuous Delivery on Azure
Continuous Delivery on Azure
Add Flask Started Code to project
Replace scaffolding code with Flask Machine Learning code
Authorize Azure App Service
Enable continuous deployment with Azure Pipelines
Checkin Azure Pipelines YAML based config file into Github
Enable Github + Azure Pipelines
Successful deployment of the project in Azure Pipelines.
Verify Prediction with starter code file make_predict_azure_app.sh
Documentation of Work
Document Work in Github
Creating project plan
Creating Trelo board
Create Architecture Diagram
Complete all of the TODOs in the template README.md file
Demo of Work for Submission
Final Demo of Projectby video
Create final video of project
You uploaded the video to YouTube (or a similar service) and added the link to your README
Review Feedback and do corrective actions based on Feedback
Project Review Feedback
Project Clean up
Clean up Azure Resources
Delete pipeline
Delete azure app services
Formulas:
Start = [Week]
Start = [End, row above]+1
End = [Week, row below]-1
Week = [Week, row above]+7

## Param
To Do
In Progess
Done